## Sheet1
Story ID | Story Name | Description | Priority | Iteration (Sprint) number | Acceptance Criteria | Estimation | Notes | Date started (or planned) | Date finished (or planned)
US001 | User login | As a user (TA, MO, or Admin), I want to log in with my email and password so that I can access my role-specific dashboard. | Must | 1 | 1. Login page with email and password fields. 2. Valid credentials redirect to role dashboard (TA/MO/Admin). 3. Invalid credentials show error message. 4. User data stored in users.json. | 3 |  | 2026-03-09 | 2026-03-21
US002 | TA registered an account | As a new TA applicant, I want to register an account so that I can use the system. | Must | 1 | 1. Registration page: name, student ID, email, password, confirm password. 2. Email must be unique; duplicate email error. 3. Passwords must match. 4. Account saved to users.json with role "TA". 5. Success message and redirect to login. | 2 |  | 2026-03-09 | 2026-03-21
US003 | Create TA profile | As a TA applicant, I want to create a personal profile with my basic information so that I can provide necessary details for job applications. | Must | 1 | 1. From TA dashboard, access "My Profile" to input: name, student ID, email, major, GPA, skills (tags). 2. Required fields: name, student ID, email, major; validation on submit. 3. Data saved to profiles.json linked to user ID. 4. Success message. | 3 |  | 2026-03-09 | 2026-03-21
US004 | Upload resume | As a TA applicant, I want to upload my CV to my profile so that MOs can review my qualifications. | Must | 1 | 1. On profile page, upload PDF option. 2. Only PDF files accepted; otherwise error. 3. File saved to /cvs folder, filename based on user ID. 4. File path stored in profiles.json. 5. Upload success indicator. | 2 |  | 2026-03-09 | 2026-03-21
US005 | Recruit a teaching assistant | As a Module Organiser, I want to post a new TA job with details so that I can attract suitable applicants. | Must | 1 | 1. MO dashboard: "Post New Job" form with fields: module code, module name, description, required skills (tags), number of positions, deadline. 2. All fields except description required; deadline must be future. 3. Job saved to jobs.json with unique ID, status "open". 4. Confirmation message. | 3 |  | 2026-03-09 | 2026-03-21
US006 | View available positions | As a TA applicant, I want to see all available TA jobs so that I can choose which to apply for. | Must | 2 | 1. TA dashboard: "Available Jobs" list. 2. Jobs read from jobs.json, only future deadline and status open. 3. Each job shows module name, required skills, deadline, "Apply" button. 4. Pagination optional. | 2 |  | 2026-03-09 | 2026-03-21
US007 | Apply for the position | As a TA applicant, I want to apply for a specific job so that I can be considered for the position. | Must | 2 | 1. Click "Apply" on a job → confirmation dialog. 2. Check if already applied; if so, show message. 3. Application record (user ID, job ID, date, status "Pending") saved to applications.json. 4. Confirmation message. | 3 |  | 2026-03-23 | 2026-04-11
US008 | Check application status | As a TA applicant, I want to see the status of my applications so that I can track progress. | Should | 2 | 1. TA dashboard: "My Applications" page. 2. List applications with job title, date, status (Pending/Accepted/Rejected). 3. Click job for more details. | 2 |  | 2026-03-23 | 2026-04-11
US009 | View job applicants | As a Module Organiser, I want to see a list of applicants for each of my jobs so that I can review candidates. | Must | 2 | 1. MO selects a job from their posted jobs. 2. Display applicants: name, student ID, skills, link to download CV. 3. Data from applications.json (Pending) and profiles.json. | 3 |  | 2026-03-23 | 2026-04-11
US010 | Screen applicants | As a Module Organiser, I want to accept or reject applicants so that I can finalize TA assignments. | Must | 3 | 1. On applicants list, each has "Accept" and "Reject" buttons. 2. Clicking updates status in applications.json (Accepted/Rejected). 3. If accepted, decrement job's positions; when zero, job status becomes "filled". 4. UI updates. | 3 |  | 2026-03-23 | 2026-04-11
US011 | Check workload | As an Admin, I want to see the total workload (number of accepted jobs) for each TA so that I can ensure no TA is overloaded. | Should | 3 | 1. Admin dashboard: "TA Workload" view. 2. List all TAs with count of accepted applications. 3. Sort by workload. | 3 |  | 2026-04-13 | 2026-05-02
US012 | Skill Matching Recommendation | As a Module Organiser, I want the system to recommend suitable TAs for a job based on skill matching so that I can quickly identify good candidates. | Could | 4 | 1. On job's applicants list, each applicant shows "Match Score" (percentage of required skills matched). 2. Sort by match score. 3. Score calculated by comparing required skills (job) with applicant skills (profile). | 5 |  | 2026-04-13 | 2026-05-02
US013 | Identify the missing skills of the applicant | As a system, I hope to identify the missing skills of applicants so as to provide improvement suggestions. | Could | 4 | 1. On job details page (logged in TA), show "Your skills vs. required skills". 2. List matched and missing skills. 3. Encouraging message if missing. | 5 |  | 2026/5/4 | 2026-05-23